## Summary
Project Name | : | Smart Profiling of Rice, BRRI
Project Manager | : | Mohammad Saiful Alam Khan
Project ID | :
Tester | : | SQTC Team
Test Case Preparation Date | :
Version | : | 0.1
Total scenarios | : | 0
Total Test case | : | 0
Test case with steps | : | 0
Total Passed test case | : | 98
Total Failed test case | : | 5
Total blocked test case | : | 0
Total untested | : | 0
Total | : | 103

## Test_cases
Test Case Number | Test Case Name/Title | Description | Expected Result | Actual Result | Category | Test results | Defect ID | Defect Severity | Comments | Test Data | Planned Execution Date | Actual Execution Date | Firefox | Chrome | IE | Edge | Executed By | Browser Execution By
TS001_Admin_TC001 | Login screen availability | Check if admin login screen is available | Admin login screen should be available | Admin login screen is available | Functional | Pass
TS001_Admin_TC002 | Sign in button availability | Check if the sign in button works properly | Sign in butoon should work properly and admin should sign in | Sign in button worked properly | Functional | Pass
TS001_Admin_TC003 | Remember me option availability | Check if remember me option is working properly | Remember me option shoould work properly | It worked properly | Functional | Pass
TS001_Admin_TC004 | Forgot password option availability | Check if the forgot password option is working properly | It should work properly | It did not working | Functional | Fail | 2609 | Major
Ts002_Admin_TC001 | Administrator Dashboard option in homepage availability | Check if Administrator Dashboard option is available in homepage | Administrator Dasboard option should be available in homepage | Administrator Dasboard option is available in homepage | Functional | Pass
Ts002_Admin_TC002 | Enter admin dashboard option availability | Check if the enter admin dashboard option works properly | Enter admin dasboard option should work properly and after clicking this option it should go to the login screen page | Enter Admin Dashboard option worked properly | Functional | Pass
TS003_Admin_TC001 | Expert Dashboard option in homepage availability | Check if Expert Dashboard option is available in homepage | Expert Dashboard option should be available in homepage | Expert Dashboard option is available in homepage | Functional | Pass
TS003_Admin_TC002 | Enter expert dashboard option availability | Check if enter expert dasboard option is working properly | Enter expert dasboard option should work properly and after clicking this option it should go to the login screen page | Enter Expert Dashboard option worked properly | Functional | Pass
TS004_Admin_TC001 | System Admin Dashboard option in homepage availability | Check if system admin dashboard option in homepage is working properly | System admin dashboard option in homepage should be available | System admin dashboard option in homepage is available | Functional | Pass
TS004_Admin_TC002 | Enter system admin dashboard option availability | Check if enter system admin dasboard option is working properly | Enter system admin dasboard option should work properly and after clicking this option it should go to the login screen page | Enter System Admin Dashboard option worked properly | Functional | Pass
TS005_Admin_TC001 | User Dashboard option in homepage availability | Check if user dashboard option in homepage is working properly | User dashboard option in homepage should be available | User dashboard option in homepage is available | Functional | Pass
TS005_Admin_TC002 | Enter user dashboard option availability | Check if enter user dasboard option is working properly | Enter user dasboard option should work properly and after clicking this option it should go to the login screen page | Enter User Dashboard option worked properly | Functional | Pass
TS006_Admin_TC001 | Admin Dashboard page availability | Check if admin dashboard page is available | Admin dashboard page should be available | Admin Dashboard page is available | Functional | Pass
TS006_Admin_TC002 | Theme changing option availability | Check if theme changing option is available | Theme changing option should be available | Theme changing option is available | Functional | Pass
TS006_Admin_TC003 | Shortcut option responsiveness | Check if shortcut option is responsive | Shortcut option should be responsive | Shortcut option is responsive | Functional | Pass
TS006_Admin_TC004 | Notification option availability | Check if notification option is working properly | Notification option should be work | Notification does not work | Functional | Fail | 2610 | Normal
TS006_Admin_TC005 | View all varieties in rice varieties option availability | Check if view all varieties in rice varieties option available | It should be available | It is available | Functional | Pass
TS006_Admin_TC006 | View all users in registered users option availability | Check if view all users in registered users option available | It should be available | It is available | Functional | Pass
TS006_Admin_TC007 | View all experts in experts option availability | Check if view all experts in experts option available | It should be available | It is available | Functional | Pass
TS006_Admin_TC008 | View archives in archieve option availability | Check if view archives in archives option available | It should be available | It is available | Functional | Pass
TS006_Admin_TC009 | User Registered summary reponsiveness | Check if users registerd summary is reponsive | It should be reponsive | It is responsive | Functional | Pass
TS006_Admin_TC010 | Admin profile availability | Check if admin profile is available | It should be available | It is available | Functional | Pass
TS007_Admin_TC001 | বিভাগ page Availability | Check if বিভাগ page is available | It should be available | It is available | Functional | Pass
TS007_Admin_TC002 | Edit option responsiveness in বিভাগ page | Check if edit option is responsive in বিভাগ page | It should be responsive | It is responsive | Functional | Pass
TS007_Admin_TC003 | Update button responsiveness in বিভাগ page | Check if update button is responsive in বিভাগpage | It should be responsive | It is responsive | Functional | Pass
TS007_Admin_TC004 | বিভাগ সমূহ button availability in বিভাগ page | Check if বিভাগ সমূহ button is available in বিভাগ page | It should be responsive | It is responsive | Functional | Pass
TS008_Admin_TC001 | জেলা page availability | Check if জেলা page is available | It should be available | It is available | Functional | Pass
TS008_Admin_TC002 | Edit option responsiveness in জেলা page | Check if edit option is responsive in জেলা page | It should be responsive | It is responsive | Functional | Pass
TS008_Admin_TC003 | Update button responsiveness in জেলা page | Check if update button is responsive in জেলা page | It should be responsive | It is responsive | Functional | Pass
TS008_Admin_TC004 | জেলা যুক্ত করুন button responsive | Check if জেলা যুক্ত করুন button is responsive | It should be responsive | It is responsive | Functional | Pass
TS008_Admin_TC005 | জেলা সমূহ button responsiveness in জেলা page | Check if জেলা সমূহ button responsive | It should be responsive | It is responsive | Functional | Pass
TS008_Admin_TC006 | Esterisk mark (*) availability | Check if esterisk mark(*) is available in mandatory field | It should be available | It is available | Functional | Pass
TS009_Admin_TC001 | অঞ্চল page availability | Check if অঞ্চল page is available | It should be available | It is available | Functional | Pass
TS009_Admin_TC002 | Edit option responsiveness in অঞ্চল page | Check if edit option is responsive in অঞ্চল page | It should be responsive | It is responsive | Functional | Pass
TS009_Admin_TC003 | Deposite button responsiveness in অঞ্চল page | Check if deposite button is responsive in অঞ্চল page | It should be responsive | It is responsive | Functional | Pass
TS009_Admin_TC004 | অঞ্চল যুক্ত করুন button responsive | Check if অঞ্চল যুক্ত করুন button is responsive | It should be responsive | It is responsive | Functional | Pass
TS009_Admin_TC005 | অঞ্চল সমূহ button responsiveness in জেলা page | Check if অঞ্চল সমূহ button responsive | It should be responsive | It is responsive | Functional | Pass
TS009_Admin_TC006 | Esterisk mark (*) availability | Check if esterisk mark(*) is available in mandatory field | It should be available | It is available | Functional | Pass
TS010_Admin_TC001 | উপজেলা page availability | Check if উপজেলা page is available | It should be available | It is available | Functional | Pass
TS010_Admin_TC002 | Edit option responsiveness in উপজেলা page | Check if edit option is responsive in উপজেলা page | It should be responsive | It is responsive | Functional | Pass
TS010_Admin_TC003 | অঞ্চল option responsiveness in উপজেলা page | Check if অঞ্চল option is responsive in উপজেলা page | It should be responsive | It is responsive | Functional | Pass
TS010_Admin_TC004 | Dropdown option responsiveness | Check if dropdown option is responsive | It should be responsive | It is responsive | Functional | Pass
TS010_Admin_TC005 | Search option responsiveness in উপজেলা page | Check if search option is responsive in উপজেলা page | It should be responsive | It is responsive | Functional | Pass
TS010_Admin_TC006 | উপজেলা যুক্ত করুন button responsive | Check if উপজেলা যুক্ত করুন button is responsive | It should be responsive | It is responsive | Functional | Pass
TS010_Admin_TC007 | উপজেলা সমূহ button responsiveness in উপজেলা page | Check if উপজেলা সমূহ button responsive in উপজেলা page | It should be responsive | It is responsive | Functional | Pass
TS010_Admin_TC008 | Esterisk mark (*) availability | Check if esterisk mark(*) is available in mandatory field | It should be available | It is available | Functional | Pass
TS010_Admin_TC009 | Add button responsiveness in উপজেলা page | Check if add button is responsive in উপজেলা page | It should be responsive | It is responsive | Functional | Pass
TS010_Admin_TC010 | Search button respnsiveness in উপজেলা page | Check if search button is responsive in উপজেলা page | It should be responsive | It is responsive | Functional | Pass
TS11_Admin_TC001 | ধানের ধরনসমুহ page avaiability | Check if ধানের ধরনসমুহ page is available | It should be available | It is available | Functional | Pass
TS11_Admin_TC002 | নতুন ধরন যোগ করুন button responsiveness in ধানের ধরনসমুহ page | Check if নতুন ধরন যোগ করুন button is responsive in ধানের ধরনসমুহ page | It should be responsive | It is responsive | Functional | Pass
TS11_Admin_TC003 | ধানের ধরনসমুহ button responsiveness in ধানের ধরনসমুহ page | Check if ধানের ধরনসমুহ button responsive | It should be responsive | It is responsive | Functional | Pass
TS11_Admin_TC004 | Esterisk mark (*) availability | Check if esterisk mark(*) is available in mandatory field | It should be available | It is available | Functional | Pass
TS11_Admin_TC005 | Add button responsiveness in ধানের ধরনসমুহ page | Check if add button is responsive in ধানের ধরনসমুহ page | It should be responsive | It is adding new type in the list but not showing the message | Functional | Fail | 2611 | Enhancement
TS11_Admin_TC006 | Edit option responsiveness in ধানের ধরনসমুহ page | Check if edit option is responsive in ধানের ধরনসমুহ page | It should be responsive | It is responsive | Functional | Pass
TS11_Admin_TC007 | Esterisk mark (*) availability in edit page of ধানের ধরন page | Check if esterisk mark(*) is available in mandatory field | It should be available | It is available | Functional | Pass
TS11_Admin_TC008 | Update button responsiveness in ধানের ধরনসমুহ page | Check if update button is responsive in ধানের ধরনসমুহ page | It should be responsive | It is responsive | Functional | Pass
TS11_Admin_TC009 | Delete option responsiveness in ধানের ধরনসমুহ page | Check if delete option is responsive in ধানের ধরনসমুহ page | It should be responsive | It is responsive | Functional | Pass
TS12_Admin_TC001 | ধানের তথ্যসমূহ page availability | Check if ধানের তথ্যসমূহ page is avilable | It should be available | It is available | Functional | Pass
TS12_Admin_TC002 | ধানের তথ্য যুক্ত করুন option responsiveness | Check if ধানের তথ্য যুক্ত করুন option is responsive | It should be responsive | It is responsive | Functional | Pass
TS12_Admin_TC003 | Esterisk mark (*) availability | Check if esterisk mark(*) is available in mandatory field | It should be available | It is available | Functional | Pass
TS12_Admin_TC004 | Add button responsiveness in ধানের তথ্য যুক্ত করুন page | Check if add button is responsive in ধানের তথ্য যুক্ত করুন page | It should be responsive | It is responsive | Functional | Pass
TS12_Admin_TC005 | Edit option responsiveness in ধানের তথ্যসমূহ page | Check if edit option is responsive in ধানের তথ্যসমূহ page | It should be responsive | It is responsive | Functional | Pass
TS12_Admin_TC006 | Esterisk mark (*) availability in edit page of ধানের তথ্যসমূহ page | Check if esterisk mark(*) is available in mandatory field | It should be available | It is available | Functional | Pass
TS12_Admin_TC007 | Update button responsiveness in ধানের তথ্যসমূহ page | Check if update button is responsive in ধানের তথ্যসমূহ page | It should be responsive | It is responsive | Functional | Pass
TS12_Admin_TC008 | Delete option responsiveness in ধানের তথ্যসমূহ page | Check if delete option is responsive in ধানের তথ্যসমূহ page | It should be responsive | It shows error | Functional | Fail | 2612 | Major
TS13_Admin_TC001 | উপযুক্ত এলাকা page availability | Check if উপযুক্ত এলাকা page is available | It should be available | It is available | Functional | Pass
TS13_Admin_TC002 | Edit option responsiveness in উপযুক্ত এলাকা page | Check if edit option is responsive in উপযুক্ত এলাকা page | It should be responsive | It is responsive | Functional | Pass
TS13_Admin_TC003 | Add button responsiveness in উপযুক্ত এলাকা page | Check if add button is responsive in উপযুক্ত এলাকা page | It should be responsive | It is responsive | Functional | Pass
TS14_Admin_TC001 | ধানের মৌসুম page availability | Check if ধানের মৌসুম page is available | It should be available | It is available | Functional | Pass
TS14_Admin_TC002 | Edit option responsiveness in ধানের মৌসুম page | Check if edit option is responsive in ধানের মৌসুম page | It should be responsive | It is responsive | Functional | Pass
TS14_Admin_TC003 | Add button responsiveness in ধানের মৌসুম page | Check if add button is responsive in ধানের মৌসুম page | It should be responsive | It is responsive | Functional | Pass
TS15_Admin_TC001 | ধানের শস্য বিন্যাস page availability | Check if ধানের শস্য বিন্যাস page is available | It should be available | It is available | Functional | Pass
TS15_Admin_TC002 | Edit option responsiveness in ধানের শস্য বিন্যাস page | Check if edit option is responsive in ধানের শস্য বিন্যাস page | It should be responsive | It is responsive | Functional | Pass
TS15_Admin_TC003 | Add button responsiveness in ধানের শস্য বিন্যাস page | Check if add button is responsive in ধানের শস্য বিন্যাস page | It should be responsive | It is responsive | Functional | Pass
TS16_Admin_TC001 | জমির ধরণ page availability | Check if জমির ধরণ page is available | It should be available | It is not available | Functional | Fail | 2613 | Major
TS17_Admin_TC001 | BRRI ধানের জাত page availability | Check if BRRI ধানের জাত page is available | It should be available | It is available | Functional | Pass
TS17_Admin_TC002 | Edit option responsiveness in BRRI ধানের জাত page | Check if edit option is responsive in BRRI ধানের জাত page | It should be responsive | It is responsive | Functional | Pass
TS17_Admin_TC003 | Esterisk mark (*) availability | Check if esterisk mark(*) is available in mandatory field | It should be available | It is available | Functional | Pass
TS17_Admin_TC004 | Add button responsiveness in BRRI ধানের জাত page | Check if add button is responsive in BRRI ধানের জাত page | It should be responsive | It is responsive | Functional | Pass
TS17_Admin_TC005 | Delete option responsiveness in BRRI ধানের জাত page | Check if delete option is responsive in BRRI ধানের জাত page | It should be responsive | It is responsive | Functional | Pass
TS18_Admin_TC001 | Archives page availability | Check if Archives page is available | It should be available | It is available | Functional | Pass
TS18_Admin_TC002 | Edit option responsiveness in Archives page | Check if edit option is responsive in Archives page | It should be responsive | It is responsive | Functional | Pass
TS18_Admin_TC003 | Add button responsiveness in Archives page | Check if add button is responsive in Archives page | It should be responsive | It is responsive | Functional | Pass
TS18_Admin_TC004 | Download option responsiveness in Archives page | Check if Download option is responsive in Archives page | It should be responsive | It is responsive | Functional | Pass
TS19_Admin_TC001 | BRRI Crop Problem page availability | Check if BRRI Crop Problem page is available | It should be available | It is available | Functional | Pass
TS19_Admin_TC002 | Edit option responsiveness in BRRI Crop Problem page | Check if edit option is responsive in BRRI Crop Problem page | It should be responsive | It is responsive | Functional | Pass
TS19_Admin_TC003 | Search button responsiveness in BRRI Crop Problem page | Check if search button is responsive in BRRI Crop Problem page | It should be responsive | It is responsive | Functional | Pass
TS20_Admin_TC001 | Chat page availability | Check if Chat page is available | It should be available | It is available | Functional | Pass
TS20_Admin_TC002 | Reply option responsiveness in Chat page | Check if reply option is responsive in Chat page | It should be responsive | It is responsive | Functional | Pass
TS20_Admin_TC003 | Search button responsiveness in Chat page | Check if search button is responsive in Chat page | It should be responsive | It is responsive | Functional | Pass
TS21_Admin_TC001 | ধান চাষ page availability | Check if ধান চাষ page is available | It should be available | It is available | Functional | Pass
TS21_Admin_TC002 | Edit option responsiveness in ধান চাষ page | Check if edit option is responsive in ধান চাষ page | It should be responsive | It is responsive | Functional | Pass
TS21_Admin_TC003 | Add button responsiveness in ধান চাষ page | Check if add button is responsive in ধান চাষ page | It should be responsive | It is responsive | Functional | Pass
TS22_Admin_TC001 | পোকা মাকড় ব্যবস্থাপনা page availability | Check if পোকা মাকড় ব্যবস্থাপনা page is available | It should be available | It is available | Functional | Pass
TS22_Admin_TC002 | Edit option responsiveness in পোকা মাকড় ব্যবস্থাপনা page | Check if edit option is responsive in পোকা মাকড় ব্যবস্থাপনা page | It should be responsive | It is responsive | Functional | Pass
TS22_Admin_TC003 | Add button responsiveness in পোকা মাকড় ব্যবস্থাপনা page | Check if add button is responsive in পোকা মাকড় ব্যবস্থাপনা page | It should be responsive | It is responsive | Functional | Pass
TS23_Admin_TC001 | পানির সেচ প্রকল্প ব্যবস্থাপনা page availability | Check if পানির সেচ প্রকল্প ব্যবস্থাপনা page is available | It should be available | It is available | Functional | Pass
TS23_Admin_TC002 | Edit option responsiveness in পানির সেচ প্রকল্প ব্যবস্থাপনা page | Check if edit option is responsive in পানির সেচ প্রকল্প ব্যবস্থাপনা page | It should be responsive | It is responsive | Functional | Pass
TS23_Admin_TC003 | Add button responsiveness in পানির সেচ প্রকল্প ব্যবস্থাপনা page | Check if add button is responsive in পানির সেচ প্রকল্প ব্যবস্থাপনা page | It should be responsive | It is responsive | Functional | Pass
TS24_Admin_TC001 | মাটি সার ব্যবস্থাপনা page availability | Check if মাটি সার ব্যবস্থাপনা page is available | It should be available | It is available | Functional | Pass
TS24_Admin_TC002 | Edit option responsiveness in মাটি সার ব্যবস্থাপনা page | Check if edit option is responsive in মাটি সার ব্যবস্থাপনা page | It should be responsive | It is responsive | Functional | Pass
TS24_Admin_TC003 | Add button responsiveness in মাটি সার ব্যবস্থাপনা page | Check if add button is responsive in মাটি সার ব্যবস্থাপনা page | It should be responsive | It is responsive | Functional | Pass
TS24_Admin_TC004 | Search button responsiveness in মাটি সার ব্যবস্থাপনা page | Check if search button is responsive in মাটি সার ব্যবস্থাপনা page | It should be responsive | It is responsive | Functional | Pass

## Review Comment
SL No | Document name | Section name | Review Comment | Author name | Solution | Review Comment | Reviewed By | Reviewed Date | Status

## Test steps
Test Case Number | Test Step ID | Test Steps | Expected Result | Test Results | Test Data
TS001_Admin_TC004 | 1 | Open browser and enter URL (https://brri.tk/admin/login) | Forgot password page should be available | Page not found
| 2 | Click on forgot password
TS006_Admin_TC004 | 1 | Open browser and enter URL (https://brri.tk/admin/login) | Notification details should be shown after clicking the notification | Notification details are not shown
| 2 | Enter valid Credential for admin user( User name: admin@gmail.com Password:12345678
| 3 | Click on notification button
| 4 | click on any notification
TS11_Admin_TC005 | 1 | Open browser and enter URL (https://brri.tk/admin/login) | Added massage should be shown before adding the list | Added new rice type in the list but showed the error after clicking submit.
| 2 | Enter valid Credential for admin user( User name: admin@gmail.com Password:12345678
| 3 | Click on ধানের ধরনসমুহ option
| 4 | Click on add button
| 5 | fill the field
| 6 | Click on submit button
TS12_Admin_TC008 | 1 | Open browser and enter URL (https://brri.tk/admin/login) | Selected information should be deleted | Error massage was showed
| 2 | Enter valid Credential for admin user( User name: admin@gmail.com Password:12345678
| 3 | Click on ধানের তথ্যসমূহ option
| 4 | Click on delete option
| 5 | Click on ok
TS16_Admin_TC001 | 1 | Open browser and enter URL (https://brri.tk/admin/login) | Page should be found | Page not found
| 2 | Enter valid Credential for admin user( User name: admin@gmail.com Password:12345678
| 3 | Click on জমির ধরণ

## Defect-In-BugZilla
Bug ID | Component | Severity | Status | Resolution | Summary | Actual Result | Expected Result | Steps TO Reproduce | TC No. | Attachment
2601 | Admin | enhancement | CONFIRMED | --- | Smart Pofiling of Rice Home page¦¦ à¦¬à§€à¦œ à¦‰à§Žà¦ªà¦¾à¦¦à¦¨ à¦“ à¦¸à¦‚à¦°à¦•à§à¦·à¦£ page¦¦Admin user cannot search
2602 | Admin | enhancement | CONFIRMED | --- | Smart Pofiling of Rice Home page¦¦ à¦¬à§€à¦œ à¦‰à§Žà¦ªà¦¾à¦¦à¦¨ à¦“ à¦¸à¦‚à¦°à¦•à§à¦·à¦£ page¦¦Admin user cannot edit
2603 | Admin | enhancement | CONFIRMED | --- | Smart Pofiling of Rice Home page¦¦ à¦¬à§€à¦œ à¦‰à§Žà¦ªà¦¾à¦¦à¦¨ à¦“ à¦¸à¦‚à¦°à¦•à§à¦·à¦£ page¦¦Admin user cannot delete
2604 | System Admin | enhancement | CONFIRMED | --- | Smart Pofiling of Rice login¦¦ System admin Login Page¦¦ Systemadmin forgot password is not working
2605 | System Admin | major | CONFIRMED | --- | Smart Pofiling of Rice login¦¦ System admin Home Page¦¦ Systemadmin Dashboard content is not functional
2606 | System Admin | minor | CONFIRMED | --- | Smart Pofiling of Rice login¦¦ System admin Home Page¦¦ Systemadmin data table option is empty
2607 | System Admin | minor | CONFIRMED | --- | Smart Pofiling of Rice login¦¦ System admin Home Page¦¦ Systemadmin Systemadmin slick slider option is empty
2608 | System Admin | minor | CONFIRMED | --- | Smart Pofiling of Rice login¦¦ System admin Home Page¦¦ Systemadmin Blank option is empty
2609 | Admin | major | CONFIRMED | --- | Admin¦¦Login¦¦Forgot password page is not found
2610 | Admin | normal | CONFIRMED | --- | Admin¦¦Homepage¦¦ Notification details not shown
2611 | Admin | enhancement | CONFIRMED | --- | Admin¦¦সাধারন তথ্য¦¦Added new rice type in the list but showed the error after clicking submit.
2612 | Admin | major | CONFIRMED | --- | Admin¦¦ধানের তথ্যসমূহ¦¦ Selected information is not deleted.
2613 | Admin | major | CONFIRMED | --- | Admin¦¦জমির ধরণ¦¦ Page not found

## Test_Scenarios
Test Scenario No. | Module | User Type | SubModule | Sub-Submodule | Sub-Sub-Submodule | Test Scenario | TC | POC | Priority | Planned Execution Date | Actual Execution Date
TS001 | Admin | Super Admin | Login Screen |  |  | Verify UI and functionality for Login Screen | 4 |  | High
TS002 | Admin | Super Admin | Homepage | Administrator Dashboard |  | Verify UI and functionality for Administrator Dashboard
TS003 | Admin | Super Admin | Homepage | Expert Dashboard |  | Verify UI and functionality for Expert Dashboard | 2 |  | High
TS004 | Admin | Super Admin | Homepage | System Admin Dashboard |  | Verify UI and functionality for System Admin Dashboard | 2 |  | High
TS005 | Admin | Super Admin | Homepage | User Dashboard |  | Verify UI and functionality for User Dashboard | 2 |  | High
TS006 | Admin | Super Admin | Administrator Dashboard |  |  | Verify UI and functionality for Administrator Dashboard | 10 |  | High
TS007 | Admin | Super Admin | সাধারন তথ্য | বিভাগ |  | Verify UI and functionality for বিভাগ | 4 |  | High
TS008 | Admin | Super Admin | সাধারন তথ্য | জেলা |  | Verify UI and functionality for জেলা | 6 |  | High
TS009 | Admin | Super Admin | সাধারন তথ্য | অঞ্চল |  | Verify UI and functionality for অঞ্চল | 6 |  | High
TS010 | Admin | Super Admin | সাধারন তথ্য | উপজেলা |  | Verify UI and functionality for উপজেলা | 10 |  | High
TS011 | Admin | Super Admin | সাধারন তথ্য | ধানের ধরনসমুহ |  | Verify UI and functionality for ধানের ধরনসমুহ | 0 |  | High
TS012 | Admin | Super Admin | Rice | ধানের তথ্যসমূহ |  | Verify UI and functionality for ধানের তথ্যসমূহ | 0 |  | High
TS013 | Admin | Super Admin | Rice | উপযুক্ত এলাকা |  | Verify UI and functionality for উপযুক্ত এলাকা | 0 |  | High
TS014 | Admin | Super Admin | Rice | মৌসুম |  | Verify UI and functionality for মৌসুম | 0 |  | High
TS015 | Admin | Super Admin | Rice | শস্য বিন্যাস |  | Verify UI and functionality for শস্য বিন্যাস | 0 |  | High
TS016 | Admin | Super Admin | Rice | জমির ধরণ |  | Verify UI and functionality for জমির ধরণ | 0 |  | High
TS017 | Admin | Super Admin | Rice | BRRI ধানের জাত |  | Verify UI and functionality for BRRI ধানের জাত | 0 |  | High
TS018 | Admin | Super Admin | Rice | Archives |  | Verify UI and functionality for Archives | 0 |  | High
TS019 | Admin | Super Admin | Rice | BRRI Crop Problem |  | Verify UI and functionality for BRRI Crop Problem | 0 |  | High
TS020 | Admin | Super Admin | Chat |  |  | Verify UI and functionality for Chat | 0 |  | High
TS021 | Admin | Super Admin | ধান চাষ |  |  | Verify UI and functionality for ধান চাষ | 0 |  | High
TS022 | Admin | Super Admin | পোকা মাকড় ব্যবস্থাপনা |  |  | Verify UI and functionality for পোকা মাকড় ব্যবস্থাপনা | 0 |  | High
TS023 | Admin | Super Admin | পানির সেচ প্রকল্প |  |  | Verify UI and functionality for পানির সেচ প্রকল্প | 0 |  | High
TS024 | Admin | Super Admin | মাটি সার ব্যবস্থাপনা |  |  | Verify UI and functionality for মাটি সার ব্যবস্থাপনা | 0 |  | High
TS025 | Admin | Super Admin | বীজ উৎপাদন ও সংরক্ষণ |  |  | Verify UI and functionality for বীজ উৎপাদন ও সংরক্ষণ | 0 |  | High
TS026 | Admin | Super Admin | রোগ বালাই ব্যবস্থাপনা |  |  | Verify UI and functionality for রোগ বালাই ব্যবস্থাপনা | 0 |  | High
TS027 | Admin | Super Admin | নোটিফিকেশন সমূহ |  |  | Verify UI and functionality for নোটিফিকেশন সমূহ | 0 |  | High
TS028 | Admin | Super Admin | All Types of Users | Manage Users |  | Verify UI and functionality for Manage Users | 0 |  | High
TS029 | Admin | Super Admin | All Types of Users | Generate Report |  | Verify UI and functionality for Generate Report | 0 |  | High
TS030 | Admin | Super Admin | All Types of Users | User Report |  | Verify UI and functionality for User Report | 0 |  | High
TS031 | Admin | Super Admin | All Types of Users | Manage Experts |  | Verify UI and functionality for Manage Experts | 0 |  | High
TS032 | Admin | Super Admin | All Types of Users | Manage System Admin |  | Verify UI and functionality for Manage System Admin | 0 |  | High
TS033 | User | User | Login Screen |  |  | Verify UI and functionality for login screen |  |  | High
TS034 | User | User | Dashboard |  |  | Verify UI and functionality for Dashboard |  |  | High
TS035 | User | User | More | ফসলের সমস্যার কথা জানান |  | Verify UI and functionality for ফসলের সমস্যার কথা জানান |  |  | High
TS036 | User | User | More | BRRI Crop Problem |  | Verify UI and functionality for BRRI Crop Problem |  |  | High
TS037 | User | User | More | COMPARE |  | Verify UI and functionality for Compare |  |  | High
TS038 | User | User | More | Chat |  | Verify UI and functionality for Chat |  |  | High
TS039 | User | User | More | Calculation |  | Verify UI and functionality for Calculation |  |  | High
TS040 | Expert | Expert | Login Screen |  |  | Verify UI and functionality for login Screen |  |  | High
TS041 | Expert | Expert | Dashboard |  |  | Verify UI and functionality for Dashboard |  |  | High
TS042 | Expert | Expert | More | Crop Problems |  | Verify UI and functionality for Crop Problems |  |  | High
TS043 | System Admin | System Admin | Login Screen |  |  | Verify UI and functionality for Login Screen |  |  | High
TS044 | System Admin | System Admin | Dashboard |  |  | Verify UI and functionality for Dashboard |  |  | High
TS045 | System Admin | System Admin | Various | Example | Data-Table | Verify UI and functionality for Data Table |  |  | High
TS046 | System Admin | System Admin | Various | Example | Slick Slider | Verify UI and functionality for Slick Slider |  |  | High
TS047 | System Admin | System Admin | Various | Example | Blank | Verify UI and functionality for Blank |  |  | High
TS048 | Mobile App User | User | Login Screen
TS049 | Mobile App User | User | OTP submission page
TS050 | Mobile App User | User | Homepage | ধানের জাত পরিচিতি
TS051 | Mobile App User | User | Homepage | বিভিন্ন ধরনের চাষপদ্ধতি
TS052 | Mobile App User | User | Homepage | মাটি ও সার ব্যবস্থাপনা
TS053 | Mobile App User | User | Homepage | ধানের জাত নির্বাচন
TS054 | Mobile App User | User | Homepage | সেচ ও পানি ব্যবস্থাপনা
TS055 | Mobile App User | User | Homepage | রোগ-বালাই ব্যবস্থাপনা
TS056 | Mobile App User | User | Homepage | পোকামাকড় ব্যবস্থাপনা
TS057 | Mobile App User | User | Homepage | বীজ উৎপাদন
TS058 | Mobile App User | User | Homepage | সম্ভাব্য খরচ নির্ণয়
TS059 | Mobile App User | User | Homepage | ফসলের সমস্যার কথা জানান
TS060 | Mobile App User | User | Homepage | আবহাওয়া আপডেট
TS061 | Mobile App User | User | Homepage | আর্কাইভ
TS062 | Mobile App User | User | Chat
TS063 | Mobile App User | User | Problem
TS064 | Mobile App User | User | See More | Edit and Update Profile
TS065 | Mobile App User | User | See More | ব্রি পরিচিতি
TS066 | Mobile App User | User | See More | ভাষা পরিবর্তন
TS067 | Mobile App User | User | See More | যোগাযোগ
TS068 | Mobile App User | User | See More | রেটিং প্রদান করুন
TS069 | Mobile App User | User | See More | সার্বিক সহযোগিতা
TS070 | Mobile App User | User | See More | গোপনীয়তা নীতি
TS071 | Mobile App User | User | See More | লগ আউট করুন
TS072 | Mobile App User | User | See More | Notification
|  | Total TC Written | 103
|  | Pass | 98
|  | Fail | 5
|  | Blocked | 0
|  | Untested | 0
|  | Skipped | 0
|  | Total Executed | 103

## Tracability Matrix
SNO | Requirement ID | Test Scenario | TestCase | Count